## Sheet1
Oakthorpe Donisthorpe and Acresford Parish Council Proposed projects
Project | Priority | Notes |  |  | Lead Cllr | Updated for 13/4/22 meeting
OCLC MUGA surface replacement | High | Grant application |  |  | DW | Planning approval required prior to funding being approved
OCLC MUGA fencing to be increased in height | High | Grant application |  |  | DW | in process
OCLC MUGA floodlights to be replaced with energy efficient type | Medium | Grant application |  |  |  | in process
Ramscliffe football pitch drainage improvments | Medium | Grant application |  |  |  | not started
Oakthorpe Play Area replace mesh fencing with railings and install gate as recommended | Medium | Funding to be released from housing development |  |  |  | not started, 1st house occupied, clerk now contacted NWLDC
Oakthorpe Play Area Improve age range of equipment | Medium | Funding to be released from housing development |  |  |  | not started
OCLC replace hedging with fencing to improve visibility | Low | Review |  |  |  | review
Parish Memorial benches | medium | Grant appplication to IM |  | N A-H lead cllr | N A-H | Completed £2000 approved
Improve welcome at entrances to the parish with planters or alternative | low | subject to finances, plan over 5 years |  |  |  | not started
Review and replace notice boards as necessary to imrpvoe appearance and ease of use | Low | Ivy Close completed | To indentify and prioritise other boards |  | SMcK | completed
OCLC notice board at entrance. | Low | New notice board needed |  |  | CK | negotiations with LCC on repair
Donisthorpe Hill Street railings clean and repaint | medium | Reported to Cllr Ashman for Highways attention with request to be added to programme of work. |  |  | SMcK | confirmation of work on programme needed
Acresford a444 MVAS | High | Completed |  |  | DG | Completed
OCLC upgrade CCTV | Medium | Review |  |  |  | Review
Wildflower verges | medium | Oakthorpe alongside New St, Acresford corner area, Donisthorpe Acresford Road/Hill St |  |  | SMcK | Spring bulb planting ongoing annually
Day of Reflection 23rd March 2022 | High | Rainbow Bench and a Flowering Cherry Tree, one per village |  |  | SMc K | Bases in place, trees planted
War Memorial Gates | Medium | Application to War Memorial Trust for grant |  |  | SMcK | in process
MVAS to existing psosts on Measham Road Oakthorpe | High | LCC to remove flashing signs and replace with MVAS |  |  | MW | Not started, awaiting approval from LCC
Queens Platinum Jubilee | High | Identfiy and purchase souvenir for all children attending the 2 local schools in the parish |  |  | SMcK | completed
Community Service Award | High | Identify options for annual award to individuals/group who provide services of beneift to the parish |  |  | DW/JA | in process